## Sheet1
James Kathrein Hub Project Hardware Design Plan
Sr.no | Milestones | ETA (Days) | Cost (USD)
1 | R&D (Requirments, Refernce Designs , Datasheet , Block Diagram) | 1 | 0
2 | Library Creation | 5 | 0
3 | Validation of Libraries (IPC7351B and MFR standards) | 1 | 0
4 | Schematic Deveopment (Altium) | 15 | 1900
5 | Schematic Verification | 2 | 0
6 | PCB Intial Kickoff | 1 | 0
7 | Highspeed and Impedence control Calculations | 1 | 0
8 | Placement and Board Dimensions | 4 | 1500
9 | Layer Stackup and Rules set (JLCPCB or PCBway Compatible) | 1 | 0
10 | Verification of PCB Layout | 2 | 0
11 | Documentation (PCB assembly and Mechanical Integration) | 1 | 100
12 | Fabrication and Deliverables (Gerbers Files , Pick and Place Files , BOM , PDFs) | 1 | 100
|  | 35 | 3600